## Jira
Backlog
Summary | Issue key | Priority | Story points | Epics | Search Bar |  | Graph |  | V. Credits |  | Register & Sign in
log out of my account to have access to other accounts I have created | LEMO-57 | High | 3 | Account | LEMO-35 |  | LEMO-42 |  | LEMO-52 |  | LEMO-57
change my password to adhere to proper security protocols | LEMO-56 | Medium | 1 | Account | LEMO-34 |  | LEMO-32 |  | LEMO-43 | done | LEMO-54
make an account to access the app and save my information | LEMO-54 | High | 8 | Account | LEMO-30 |  | LEMO-26 | done | LEMO-38 |  | LEMO-45 | done
look at my stock order history to be able to see how many shares I have bought & sold over time | LEMO-53 | Medium | 5 | Account | LEMO-31
change my email to adhere to proper security protocols | LEMO-51 | Low |  | Account
change my display name & profile picture for fun | LEMO-50 | Low | 3 | Account | P. Dashboard |  | S. Dashboard |  | G. User Account |  | P. User Account
erase my account so that i can start a new portfolio from the ground up | LEMO-49 | Medium | 2 | Account | LEMO-55 |  | LEMO-37 |  | LEMO-56 |  | LEMO-53
permanently delete my account to remove all personal info in the case where i no longer want to use the app | LEMO-47 | Medium | 2 | Account | LEMO-48 |  | LEMO-33 |  | LEMO-51 |  | LEMO-49
sign into my account to access the app & look at my info | LEMO-45 | High | 5 | Account | LEMO-46 |  | LEMO-41 |  | LEMO-50
change the app's appearance to see the app in my preferred theme | LEMO-44 | Low | OOS | Account | LEMO-40 |  | LEMO-26 | done | LEMO-47
view my portfolio's net worth to see how much progress my portfolio has made | LEMO-55 | High | 3 | Portfolio | LEMO-36
buy fake stocks at their current irl equivelant price to simulate what it's like to make purchases for a real stock portfolio | LEMO-52 | High | 13 | Portfolio | LEMO-29
portfolio to update even when I am not watching it to simulate what a real stock portfolio would act like | LEMO-48 | High | 5 | Portfolio | LEMO-41
see my total dividends from each stock I have holdings in to see how much I have earned per investment | LEMO-46 | High | 5 | Portfolio
add virtual credits to my wallet so that i can purchase stocks | LEMO-43 | High | 2 | Portfolio | Release Plan
compare my portfolio to popular investment funds to see how well my portfolio is doing in comparison | LEMO-40 | Medium | 2 | Portfolio
liquidate my portfolio so that i can use my 'profits' to buy more stocks | LEMO-38 | Medium | 3 | Portfolio | Sprint 0 | Story Points | Epic | Sprint 1 | Story Points | Epic | Sprint 2 | Story Points | Epic | Sprint 3 | Story Points | Epic
see my virtual portfolio grow like a real stock portfolio to show how a portfolio would move in an irl scenario | LEMO-36 | High | 8 | Portfolio | LEMO-57 | 3 | Account | LEMO-37 | 3 | Stocks | LEMO-42 | 8 | Stocks | LEMO-35 | 5 | Portfolio
search for stocks I have holdings in to find specific stocks I have invested in & check on their performance | LEMO-35 | Medium | 5 | Portfolio | LEMO-54 | 8 | Account | LEMO-33 | 5 | Stocks | LEMO-32 | 8 | Stocks | LEMO-34 | 5 | Stocks
view my portfolio's net worth to see how much progress my portfolio has made | LEMO-29 | High | 5 | Portfolio | LEMO-45 | 5 | Account | LEMO-41 | 3 | Stocks | LEMO-43 | 2 | Portfolio | LEMO-30 | 13 | Stocks
view & resize a graph displaying stock changes over a set period of time to check how much a stock has changed | LEMO-42 | High | 8 | Stocks |  |  |  | LEMO-26 | 5 | Stocks
see which stocks are performing the best to know which stocks have the highest earning potential | LEMO-37 | Medium | 3 | Stocks
add stocks to a watchlist (favourites tab) so that I can easily access stocks I'm the most interested in | LEMO-34 | Medium | 5 | Stocks | Total Pts | 16 |  | Total Pts | 16 |  | Total Pts | 18 |  | Total Pts | 23
relevant information on my dashboard to be informed on the newest info about stocks that i'm watching/tracking | LEMO-33 | High | 5 | Stocks | Sprint 4 | Story Points | Epic | Sprint 5 | Story Points | Epic | Sprint 6 | Story Points | Epics |  | Left Over
hover over specific points of the stock graph & have a popup display of its price at that specific time in the graph so that i can access patterns or previous prices of a stock more clearly | LEMO-32 | Medium | 8 | Stocks | LEMO-52 | 13 | Portfolio | LEMO-46 | 5 | Portfolio | LEMO-40 | 2 | Portfolio |  | LEMO-31
search for specific stocks to find & look at the information of said stock | LEMO-30 | High | 13 | Stocks | LEMO-48 | 5 | Portfolio | LEMO-38 | 3 | Portfolio | LEMO-49 | 2 | Account |  | LEMO-51
view a live stock display/graph so that I can track how well a stock is doing | LEMO-26 | High | 5 | Stocks | LEMO-55 | 3 | Portfolio | LEMO-36 | 8 | Portfolio | LEMO-53 | 5 | Account
navigate between app pages to be able to easily open other pages in the app | LEMO-41 | High | 3 |  |  |  |  | LEMO-47 | 2 | Account | LEMO-50 | 3 | Account
set my location so that I can purchase stocks in my local currency & see stocks relevant to my location | LEMO-39 | Low
filter stock searchs by categories to more easily find specific stocks | LEMO-31 | Low |  |  | Total Pts | 21 |  | Total Pts | 18 |  | Total Pts | 12
Total Story Points |  |  | 130